BUILDING YOUR PDT CHARTER A guide for PMs establishing a Project Delivery Team (PDT) Charter for the first time PDBP Phase: Initiation ¦ Governed by: PROC2020 ¦ Reference: Engineer Manual (EM) 5-1-11

KEY PRINCIPLE The charter is not a formality — it is the document that gives you authority as PM. Without a current, complete charter, every decision you make is on uncertain ground.

WHAT IS THE PDT CHARTER — AND WHY IT MATTERS

The PDT Charter is the founding document of the Project Delivery Team. It establishes who is on the team, what each member is authorized to do, and who owns every significant decision category. It is required under PROC2020 at project initiation and must remain current for the life of the project.

| THE CHARTER IS: ▸ The founding document of the Project Delivery Team (PDT) ▸ The source of the PM's authority — who can decide what, up to what threshold ▸ Required under PROC2020 at project initiation ▸ A living document — must be updated when the team, scope, or thresholds change ▸ The first document a new PM should read when inheriting a project ▸ The document that separates a real team from a list of names | THE CHARTER IS NOT: ▸ A one-time box to check at initiation and forget ▸ The Project Management Plan (PMP) — the charter establishes the team; the PMP governs execution ▸ A personnel action — it documents project roles, not supervisory relationships ▸ Optional — PROC2020 requires it regardless of project size ▸ Complete if the PM field says "TBD," lists a title instead of a name, or names a previous PM ▸ Sufficient if functional chief confirmation was never documented |
| --- | --- |

REQUIRED FIELDS — WHAT PROC2020 SAYS MUST BE IN YOUR CHARTER

Every PDT Charter must contain these fields. Partial completion is not compliance — a charter with missing fields leaves gaps in decision authority that will surface at the worst possible moment.

| Required Field | What It Must Contain | Why It Matters |
| --- | --- | --- |
| Project Manager (PM) | Named individual — not a title, not TBD. One person, one name. | When something goes wrong at 4pm Friday, one person owns it. That name must be in this field before the project begins. |
| Deputy Program Manager (DPM) | Named individual with portfolio oversight role and escalation authority | Establishes the PM-DPM accountability chain. Without it, escalation paths are informal and inconsistent. |
| Functional Chiefs | Named individual per discipline — not office, not branch, not "TBD" | Commits a specific person. Anonymous or position-only entries cannot be held accountable when a conflict arises. |
| Decision Authority Thresholds | Dollar and scope limits per role — what each person can approve independently | Without thresholds, every decision is either over-cleared or under-cleared. Both create risk. |
| Functional Chief Confirmation | Signed or documented confirmation from the functional supervisor of availability for the project duration | Separates a charter from a wish list. Confirms this person is actually committed — not just listed. |
| RACI Structure | Responsible, Accountable, Consulted, and Informed (RACI) designations per decision category | If three people each think they own a decision, the charter has a gap. RACI prevents that gap. |
| Project Scope Summary | Brief, plain-language description of what the project delivers | Connects the team structure to the work. Grounds the charter in the actual project. |
| Effective Date and Revision History | Date established; date, reason, and PM signature for each revision | Establishes which version governs current decisions. A charter without revision history is probably wrong. |

COMMON CHARTER GAPS — AND HOW TO FIX THEM

These are the gaps that appear most frequently in PDT Charters across USACE. Each one looks minor until a decision gets disputed — at which point the missing field becomes the entire problem.

| The Gap | What It Looks Like | What to Do |
| --- | --- | --- |
| PM field is outdated | Charter still names the previous PM after a transition | Update on day one of the assignment. This is the first action, not a later one. |
| Thresholds are missing or vague | "Approves all decisions" or a blank threshold field | Define a specific dollar amount and scope boundary for each role. Get DPM concurrence. |
| Functional chiefs listed by title only | "Structural Engineer" or "Cost Engineer" with no name | Name the individual. If the position is unfilled, document that explicitly and set a date to resolve it. |
| No functional chief confirmation | Names appear on the charter but no supervisor sign-off exists | Obtain written confirmation from each functional supervisor before the project enters Planning. |
| RACI not completed | Roles column filled; RACI columns blank or copied from a template | Walk the RACI in the kickoff meeting. Resolve every disagreement before closing the meeting. |
| Charter not updated after team change | Departed PDT member still listed; replacement not added | Treat every team change as a charter revision trigger. Update within 5 business days. |
| Revision history not maintained | A single dated version with no record of changes | Add a revision log. Note what changed, who authorized the change, and the effective date. |
| Backup PM not identified | Charter is silent on who decides when the PM is unavailable | Name a backup PM and document the conditions under which they act. Usually the DPM. |

HOW TO RUN THE CHARTER KICKOFF CONVERSATION

The charter kickoff is the first PDT meeting. Done well, it establishes accountability, surfaces conflicts early, and produces a team that has explicitly agreed on who owns what. Done poorly, it produces a document that sits in a folder until something goes wrong.

| BEFORE THE MEETING ▸ Pull any existing charter — if one exists, mark what is current and what is outdated before the meeting starts ▸ Draft a proposed Responsible, Accountable, Consulted, and Informed (RACI) for the three decision types most likely to create conflict on this project ▸ Identify which functional chiefs have not yet confirmed availability — bring that list to the meeting ▸ Know your own DPM threshold — what can you approve without escalating ▸ Review the scope summary for accuracy — the team will discuss it in the room DURING THE MEETING ▸ Read the scope summary aloud first — get explicit agreement on what the project delivers before moving to roles ▸ Name the PM field in the room — make it unambiguous who owns project outcomes ▸ Walk the RACI row by row — pause at every disagreement and resolve it before moving on ▸ Ask for confirmation on the record: "Can I document that you are confirmed for this project for the duration?" ▸ Name the backup PM — identify who decides when the PM is unavailable and document the conditions ▸ Set the revision trigger explicitly: "We will update this charter if the PM changes, the scope changes, or any functional chief changes" AFTER THE MEETING ▸ Circulate the draft charter within 24 hours — while the conversation is fresh ▸ Collect documented confirmation from each functional supervisor within the week ▸ File the signed charter where the full PDT can access it — not just the PM's folder ▸ Put the first revision review on the calendar — 90 days is a reasonable starting cadence | THREE QUESTIONS THAT SURFACE HIDDEN GAPS 1. "Who can approve a scope change under $50K?" ▸ If you get more than one answer — your thresholds are not documented ▸ If no one answers — your thresholds do not exist ▸ If the answer is "it depends" — ask what it depends on, and document that. 2. "If the PM is unavailable, who decides?" ▸ Most charters do not answer this — the answer should be documented, not improvised ▸ Name a backup. Document the conditions under which the backup acts ▸ Confirm the backup has the authority to act — not just the willingness. 3. "Has each functional chief confirmed with their supervisor?" ▸ If the answer is "I think so" — the confirmation is not documented ▸ Confirmation means the supervisor committed them, not that they agreed themselves ▸ Ask for written confirmation — an email is sufficient; a verbal assumption is not. WHEN THE KICKOFF GETS HARD ▸ Disagreement on RACI ownership: hold the disagreement in the room. Do not table it. Unresolved RACI disputes become scope conflicts. ▸ Functional chief not yet assigned: document the gap explicitly. "Position TBD — to be filled by [date]." Do not leave it blank. ▸ Functional supervisor refuses to confirm in writing: escalate to the Deputy Program Manager (DPM). An unconfirmed commitment is a risk on your register. ▸ Previous PM disputes the update: the charter follows the project, not the person. Update it and document when the transition occurred. |
| --- | --- |

UNDERSTANDING THE RACI STRUCTURE

The Responsible, Accountable, Consulted, and Informed (RACI) structure is the most frequently misunderstood section of the PDT Charter. Getting it right eliminates the most common source of team conflict on USACE projects.

| THE FOUR RACI ROLES R — Responsible Does the work. The person who executes the task or produces the deliverable. There can be more than one R for a task, but every task needs at least one. A — Accountable Owns the outcome. Signs off on the work. There must be exactly one A per decision or deliverable — never zero, never two. The A is the person whose phone rings when something goes wrong. C — Consulted Provides input before the decision is made. Two-way communication. The C's input must be sought — not optional. I — Informed Receives notification after the decision is made. One-way communication. The I does not need to act — they need to know. | RACI FOR COMMON USACE DECISIONS Decision; R; A; C; I. Scope change under PM threshold; PM; PM; DPM, FC; Sponsor. Scope change above PM threshold; PM; DPM; FC, PM; Sponsor. Schedule rebaseline; Scheduler; PM; DPM, FC; Sponsor. Cost estimate revision; Cost Eng.; PM; DPM; Sponsor. A-E design acceptance; TL; PM; FC; DPM. Contractor change order; KO; KO; PM; DPM. Risk Register update; PM; PM; PDT; DPM. Charter revision; PM; DPM; FC; PDT. FC = Functional Chief ¦ TL = Technical Lead ¦ KO = Contracting Officer ¦ A-E = Architect-Engineer |
| --- | --- |

WHEN TO UPDATE THE CHARTER

A charter that is not kept current is a liability. These are the events that must trigger a charter revision — not "when you get around to it," but within five business days of the triggering event.

| MANDATORY REVISION TRIGGERS ▸ PM changes — the single most critical trigger. Update before the transition is complete. ▸ Any functional chief changes — departure or replacement of a named PDT member ▸ Decision authority thresholds change — new DPM guidance or re-scoped approval limits ▸ Project scope changes materially — scope additions, reductions, or redefinitions that affect team roles ▸ Functional chief confirmation lapses — person changes assignment; confirmation must be re-obtained ▸ Project transitions to a new PDBP phase — review and update the charter at each phase gate | REVISION PROCESS ▸ PM initiates the revision with a tracked change to the charter document ▸ Affected functional chiefs review and re-confirm their entries ▸ DPM reviews and approves the revised charter ▸ Revision log updated: what changed, why, effective date, PM initials ▸ Revised charter distributed to full PDT within 24 hours of DPM approval ▸ Previous version archived — not deleted. Revision history is part of the project record. 90-DAY REVIEW CADENCE Even without a triggering event, review the charter every 90 days. Ask: is every named individual still on this project? Are the thresholds still accurate? Is the scope summary current?. |
| --- | --- |

CIVIL WORKS vs. MILITARY PROGRAMS — CHARTER DIFFERENCES

| CIVIL WORKS ▸ The Project Sponsor has a formal role in the charter under the Project Partnership Agreement (PPA) ▸ Cost-sharing obligations between USACE and the non-federal sponsor must be reflected in the scope summary ▸ The District Commander or designee is typically the Accountable party for significant scope and cost changes ▸ Project Management Plan (PMP) is governed by PROC2020 and may require Headquarters review for major projects ▸ Watch for charters that do not reflect the sponsor representative — this creates ambiguity in scope decisions | MILITARY PROGRAMS ▸ The using service (Army, Air Force, etc.) installation representative often holds a PDT role — confirm their authority level ▸ The DD Form 1391 establishes the original scope — the charter scope summary must align to it ▸ Contracting Officer (KO) authority is separate from and parallel to the PM — clarify the boundary explicitly in RACI ▸ Installation personnel may rotate — functional chief confirmation lapses are more frequent and must be actively managed ▸ Programming changes can alter team composition mid-project — build revision triggers for re-programming actions into the charter |
| --- | --- |

THE PM'S CHARTER RULE If a decision is disputed and it is not in the charter — the charter is incomplete. Update it before the next decision needs to be made.