SAMPLE CHARTER — FOR TRAINING USE ONLY All names, organizations, and project details are fictitious and correspond to the Building 4521 Renovation project used in the PM in USACE case files. Use this as a reference model when completing your own PDT Charter Template.

PDT CHARTER Project Delivery Team (PDT) Charter PDBP Phase: Initiation ¦ Governed by: PROC2020 ¦ Reference: EM 5-1-11 ¦ USACE KMP-PPM

SECTION 1 — PROJECT IDENTIFICATION

| PROJECT IDENTIFICATION |  |
| --- | --- |
| Project Title | Building 4521 Renovation — Administrative Facility Upgrade |
| Project Number / Work Order | P2-123456 / WO-2026-0447 |
| Location | Fort Beaumont Military Installation, Building 4521, Beaumont, TX |
| Program Type | Military Programs — Military Construction (MILCON) |
| PDBP Phase at Charter Initiation | Initiation |
| Estimated Construction Cost | $4,750,000 |
| Funding Source / Appropriation | Military Construction, Army (MCA) — FY2026 Authorization |
| Charter Effective Date | 15 January 2026 |

SECTION 2 — PROJECT SCOPE SUMMARY

| SCOPE SUMMARY |  |
| --- | --- |
| What This Project Delivers | Design and renovate Building 4521 (45,200 SF, constructed 1987) to current Army standards. Scope includes full interior renovation of administrative spaces (Floors 1–3), replacement of HVAC, electrical distribution, and fire suppression systems, ADA compliance upgrades throughout, and exterior envelope repairs including roof replacement and window upgrades. A-E design contracted separately under existing IDIQ. Construction award targeted Q3 FY2026. |
| What Is Explicitly Out of Scope | Structural modifications beyond ADA compliance. Parking lot resurfacing (separate project P2-123457). IT/communications infrastructure (separate G6 program). Furniture, fixtures, and equipment (FF&E) beyond built-ins. Exterior landscaping. |
| Key Assumptions | Environmental clearance (Phase I ESA) complete as of 01 Dec 2025 — no remediation required. Building remains partially occupied during construction (Floors 2–3 vacated; Floor 1 active). Existing structural frame sound per 2024 structural assessment. Design funds already obligated. |
| Key Constraints | Funding ceiling: $5,100,000 total project cost (TPC) including SIOH. Required occupancy: 01 March 2027. Construction must maintain operational access to main entrance at all times. No work on federal holidays or installation training exercise blackout periods. |

SECTION 3 — PDT MEMBERSHIP AND DECISION AUTHORITY

All functional chiefs confirmed by written supervisor sign-off attached to this charter.

| PROJECT MANAGER (PM) |  |
| --- | --- |
| PM Name | Maria J. Chen |
| PM Title / Grade | Project Manager, GS-12 |
| PM Office / Phone / Email | Beaumont District, Military Programs Branch ¦ (409) 555-0147 ¦ maria.j.chen@usace.army.mil |
| PM Decision Authority Threshold | Independent approval: scope changes up to $50,000 (DPM notification within 24 hrs). Schedule changes: non-critical-path slips up to 30 calendar days. |
| PM Effective Date | 15 January 2026 |
| BACKUP PROJECT MANAGER |  |
| Backup PM Name | James R. Tran, Project Manager, GS-12 |
| Backup PM Activation Conditions | Activates when PM Chen is unavailable for 3+ consecutive business days (leave, TDY, medical). DPM notified same day. Backup PM assumes full PM decision authority during activation. |
| DEPUTY PROGRAM MANAGER (DPM) |  |
| DPM Name | Col. (Ret.) Patricia Ashford |
| DPM Office / Phone / Email | Beaumont District, Chief of Programs ¦ (409) 555-0100 ¦ patricia.ashford@usace.army.mil |
| DPM Decision Authority Threshold | Independent approval: scope changes $50,001–$500,000. Changes above $500,000 require Division Commander concurrence. All out-of-scope additions regardless of dollar value require DPM approval. |

FUNCTIONAL CHIEFS AND TEAM MEMBERS

All functional chiefs confirmed by written supervisor sign-off as of 15 January 2026.

| Role / Discipline | Named Individual | Office / Contact | Decision Authority | Confirmation |
| --- | --- | --- | --- | --- |
| Project Manager (PM) | Maria J. Chen | (409) 555-0147 | Up to $50K (Sec. 3) | N/A — PM |
| Deputy PM (DPM) | Col. (Ret.) P. Ashford | (409) 555-0100 | Up to $500K (Sec. 3) | N/A — DPM |
| Civil / Structural Engr. | Dr. Priya Nair, PE | Engr. Div. ¦ (409) 555-0212 | Structural design acceptance | Confirmed — written |
| Mechanical Engineer | Marcus T. Webb, PE | Engr. Div. ¦ (409) 555-0231 | Mechanical design acceptance | Confirmed — written |
| Electrical Engineer | Sandra K. Okonkwo, PE | Engr. Div. ¦ (409) 555-0245 | Electrical design acceptance | Confirmed — written |
| Geotechnical Engineer | Raymond Liu, PE | Engr. Div. ¦ (409) 555-0218 | Geotech findings and recs | Confirmed — written |
| Environmental Specialist | Theresa M. Galvez | Planning ¦ (409) 555-0190 | Environmental clearance | Confirmed — written |
| Cost Engineer | David A. Park | Programs ¦ (409) 555-0155 | IGE development and review | Confirmed — written |
| Scheduler | Aaliyah J. Brooks | Programs ¦ (409) 555-0162 | Schedule baseline | Confirmed — written |
| Real Estate Specialist | Frank O. Nguyen | Real Estate ¦ (409) 555-0178 | Easements and access | Confirmed — written |
| Contracting Officer (KO) | Margaret C. Torres | Contracting ¦ (409) 555-0133 | Contract award and mods | Confirmed — written |
| QA Representative | Cpl. (Ret.) D. Hughes | Resident Office ¦ (409) 555-0301 | Construction QA | Confirmed — written |
| Safety Officer | Ingrid S. Petrov | Safety ¦ (409) 555-0320 | Safety plan review | Confirmed — written |
| Sponsor / User Rep. | Maj. Kevin O'Brien | Fort Beaumont DPW ¦ (409) 555-0410 | Operational req. sign-off | Confirmed — written |

SECTION 4 — DECISION AUTHORITY THRESHOLDS

| INDEPENDENT APPROVAL AUTHORITY BY DECISION TYPE |  |
| --- | --- |
| Scope Changes — PM Threshold | Up to $50,000 cumulative per modification action. PM notifies DPM in writing within 24 hours. Modifications that change the authorized project description require DPM approval regardless of dollar value. |
| Scope Changes — DPM Threshold | $50,001 to $500,000. Changes above $500,000 require Division Commander concurrence and HQ notification per PROC2020. |
| Schedule Changes — PM Authority | Non-critical-path activity slips up to 30 calendar days without DPM approval. Any slip affecting the critical path or contract completion date requires DPM notification within 48 hours and written approval within 5 business days. |
| Cost Estimate Revisions — PM | PM may revise the IGE up to 5% of current estimate without DPM approval, provided the revision does not exceed the programmed ceiling. Revisions exceeding 5% or the ceiling require DPM approval. |
| Contingency Draw Authority | PM may authorize contingency draws up to $25,000 per action for unforeseen conditions. Draws above $25,000 require DPM approval. Any draw reducing remaining contingency below 5% of construction contract value requires DPM notification. |
| Contract Modifications — PM Role | PM identifies and documents proposed modifications; routes to KO Torres for contracting action. PM has no independent contracting authority. KO is the sole authority for contract modifications. |
| Risk Response Activation | PM may activate Mitigate or Accept responses without DPM approval. Avoid or Transfer responses require DPM concurrence. Any response involving contract modification routes through KO Torres. |

SECTION 5 — RACI STRUCTURE

R = Responsible  |  A = Accountable (exactly one per row, highlighted green)  |  C = Consulted  |  I = Informed

| Decision / Deliverable | R — Responsible | A — Accountable | C — Consulted | I — Informed |
| --- | --- | --- | --- | --- |
| Scope change under PM threshold ($0–$50K) | PM Chen | PM Chen | DPM Ashford | Sponsor O'Brien |
| Scope change over PM threshold ($50K+) | PM Chen | DPM Ashford | FC Civil, Cost Eng. | Sponsor, KO Torres |
| Schedule rebaseline | Scheduler Brooks | PM Chen | DPM Ashford, FCs affected | Sponsor, KO Torres |
| Cost estimate (IGE) revision | Cost Eng. Park | PM Chen | DPM Ashford | Sponsor O'Brien |
| Contingency draw up to $25K | PM Chen | PM Chen | DPM (notification only) | KO Torres |
| Contingency draw over $25K | PM Chen | DPM Ashford | PM Chen, Cost Eng. | KO Torres, Sponsor |
| A-E design acceptance | TL / FC by discipline | PM Chen | FC Civil, DPM Ashford | KO Torres, Sponsor |
| Contractor change order | KO Torres | KO Torres | PM Chen, FC affected | DPM Ashford, Sponsor |
| Risk Register update | PM Chen | PM Chen | Full PDT (monthly) | DPM Ashford |
| Risk response — Mitigate/Accept | PM Chen | PM Chen | FC affected | DPM Ashford |
| Risk response — Avoid/Transfer | PM Chen | DPM Ashford | PM Chen, KO Torres | Sponsor, FC affected |
| PDT member change | PM Chen | DPM Ashford | Functional supervisor | Full PDT |
| Charter revision | PM Chen | DPM Ashford | FC affected | Full PDT |
| External stakeholder communication | PM Chen | PM Chen | DPM Ashford | KO Torres |

SECTION 6 — COMMUNICATION PLAN

| REPORTING AND COMMUNICATION |  |
| --- | --- |
| PDT Meeting Cadence | Bi-weekly (every other Wednesday, 1000–1100 CT). Full PDT attendance expected. PM chairs; agenda distributed 48 hours in advance. |
| DPM Status Report — Frequency | Monthly, submitted to DPM Ashford NLT the 5th of each month. |
| DPM Status Report — Format | CCIR #8 format. Includes EVM summary (SPI, CPI), schedule status, cost status, top 3 risks with response status, and upcoming decisions requiring DPM action. |
| Sponsor Communication — Frequency | Monthly briefing with Maj. O'Brien and Fort Beaumont DPW staff. PM Chen leads; DPM Ashford attends major milestone meetings. |
| Sponsor Communication — Contact | Maj. Kevin O'Brien, Fort Beaumont DPW ¦ (409) 555-0410 ¦ kevin.obrien@army.mil |
| Risk Register Review Cadence | Monthly — standing agenda item in bi-weekly PDT meeting (first meeting of each month). Full register review at each phase gate. |
| External Stakeholders | Fort Beaumont IMCOM — construction schedule and access impacts. Fort Beaumont Safety Office — pre-construction safety plan. State Historic Preservation Office (SHPO) — notified; no Section 106 consultation required. |

SECTION 7 — CHARTER CONFIRMATION CHECKLIST

All items confirmed as of charter effective date (15 January 2026). Charter kickoff meeting held 14 January 2026.

☑  PM name is current and reflects the individual currently assigned to this project

☑  Backup PM is named and activation conditions are documented

☑  DPM name is current

☑  All functional chiefs are named individuals — not titles or TBD

☑  PM decision authority threshold is documented with a specific dollar amount or scope boundary

☑  DPM decision authority threshold is documented with a specific dollar amount or scope boundary

☑  Functional chief confirmation obtained from each functional supervisor in writing

☑  RACI table has been walked row by row and every disagreement has been resolved

☑  Each RACI row has exactly one Accountable (A) party

☑  Scope summary is accurate and aligned to the DD Form 1391

☑  Out-of-scope items are explicitly documented

☑  Communication plan is complete and sponsor contact is confirmed

☑  Charter effective date is populated

☑  Charter distributed to all named PDT members

☑  Charter filed in the project record system (P2)

☑  First 90-day review date placed on PM calendar — 15 April 2026

SECTION 8 — REVISION LOG

| Rev # | Date | What Changed | Authorized By | PM Initials |
| --- | --- | --- | --- | --- |
| 1.0 | 15 Jan 2026 | Initial charter — original team composition. All FCs confirmed. Kickoff held 14 Jan 2026. | DPM Ashford | MJC |

SECTION 9 — SIGNATURE BLOCK

Original signed charter on file in P2 (Document ID: P2-123456-CHT-001). All signatures complete 15 January 2026.

| Role | Signature | Date | Printed Name |
| --- | --- | --- | --- |
| Project Manager (PM) | /s/ Maria J. Chen | 15 Jan 2026 | Maria J. Chen, GS-12 |
| Deputy PM (DPM) | /s/ Patricia Ashford | 15 Jan 2026 | Patricia Ashford, Col. (Ret.) |
| FC — Civil/Structural | /s/ Priya Nair | 14 Jan 2026 | Dr. Priya Nair, PE, GS-13 |
| FC — Mechanical | /s/ Marcus Webb | 14 Jan 2026 | Marcus T. Webb, PE, GS-12 |
| FC — Electrical | /s/ Sandra Okonkwo | 14 Jan 2026 | Sandra K. Okonkwo, PE, GS-12 |
| FC — Environmental | /s/ Theresa Galvez | 14 Jan 2026 | Theresa M. Galvez, GS-11 |
| Contracting Officer (KO) | /s/ Margaret Torres | 15 Jan 2026 | Margaret C. Torres, GS-13 |
| Sponsor Representative | /s/ Kevin O'Brien | 15 Jan 2026 | Maj. Kevin O'Brien, USA |

SAMPLE CHARTER — FOR TRAINING USE ONLY  |  Building 4521 Renovation — Fort Beaumont  |  USACE KMP-PPM