BUILDING YOUR PROJECT MANAGEMENT PLAN A guide for PMs developing a Project Management Plan (PMP) for the first time Project Delivery Business Process (PDBP) Phase: Initiation ¦ Governed by: PROC2020 / PROC2030 / PROC2040

KEY PRINCIPLE The PMP is not a filing artifact — it is your operating document. It should be living, current, and consulted. If it sits in a drawer, it is not doing its job.

WHAT IS THE PMP — AND WHAT IT IS NOT

| THE PMP IS: ▸ Your project's operating roadmap from initiation through closeout ▸ A living document — updated as the project evolves ▸ Required under Engineer Manual (EM) 5-1-11 and the PDBP (PROC2020) ▸ The document defining scope, schedule, cost, and how you manage each ▸ Evidence that the project was planned, not just executed | THE PMP IS NOT: ▸ A one-time document you write and file ▸ The schedule (though it references and incorporates it) ▸ A report to management — it is a tool for the PM ▸ Optional — it is required under PROC2020 ▸ Something you produce after the project is already underway |
| --- | --- |

WHEN DO YOU BUILD IT

The PMP is initiated during Initiation and refined through Planning. It is not written once — it mirrors the project lifecycle.

| Phase | Timing | Key PROC | What You Add to the PMP |
| --- | --- | --- | --- |
| Initiation | On assignment | PROC2020 | Charter, Project Delivery Team (PDT), scope statement, communication plan, initial risk log |
| Planning | Before design | PROC2030/2040 | Schedule baseline, cost estimate, resource plan, procurement strategy |
| Execution | Before award | PROC3000 | Construction management approach, Quality Assurance/Quality Control (QA/QC) plan, change management process |
| Monitoring | Ongoing | PROC3000/3010 | Earned Value Management (EVM) reporting cadence, risk register updates, change log |
| Closeout | Near project end | PROC4000 | Closeout checklist, After Action Review (AAR) approach, lessons learned process |

REQUIRED SECTIONS — WHAT YOUR PMP MUST CONTAIN

| MANAGEMENT SECTIONS ▸ Project Overview — purpose, background, location, sponsor ▸ Project Objectives — what success looks like, measurable ▸ Roles and Responsibilities — PDT RACI (Responsible, Accountable, Consulted, Informed), decision authority ▸ Communication Plan — who, what, how often, what format ▸ Change Management Process — identify, approve, document ▸ Risk Management Approach — Register maintenance and review TECHNICAL SECTIONS ▸ Scope Statement — in-scope, out-of-scope, assumptions ▸ WBS Summary — major deliverables and work packages ▸ Schedule Baseline — PROC2030-compliant, basis of estimate ▸ Cost Estimate — Independent Government Estimate (IGE), Supervision Inspection and Overhead (SIOH), contingency, funding source ▸ Procurement Strategy — contract type, acquisition approach | THREE QUESTIONS YOUR PMP MUST ANSWER 1. What are we building? ▸ Scope statement with explicit In and Out of Scope ▸ Work Breakdown Structure (WBS) that organizes scope into trackable deliverables ▸ Success criteria the sponsor would recognize 2. How are we going to build it? ▸ Schedule with critical path, float, resource loading ▸ Cost estimate with IGE, SIOH, contingency documented ▸ Procurement and contract type clearly stated 3. How will we know if we are on track? ▸ EVM metrics and reporting cadence defined ▸ Risk Register with owners and triggers maintained ▸ Change management process documented and followed |
| --- | --- |

FIVE MISTAKES FIRST-TIME PMs MAKE WITH THE PMP

| 1 | Writing it once and filing it The PMP is living. Update it when scope changes, the schedule is rebaselined, or a key risk triggers. If it is more than 90 days old without a review — it is probably wrong. |
| --- | --- |

| 2 | Confusing the PMP with the schedule The schedule answers when and how long. The PMP also answers who, what, why, and what could go wrong. A Gantt chart is not a project management plan. |
| --- | --- |

| 3 | Leaving the Out of Scope section blank "Not in scope" requires the same documentation discipline as what IS in scope. Most scope conflicts come from things one party assumed were included. Neither wrote it down. |
| --- | --- |

| 4 | Building the PMP after the project is already running If you are in construction without a current PMP — stop and write one. It is never too late to stop operating without a plan. |
| --- | --- |

| 5 | Treating it as a document for management, not for the PM The PMP is your tool. The DPM may review it — but you live in it. If you have to look up something that should be in your PMP, that is a signal the PMP is incomplete. |
| --- | --- |

YOUR FIRST WEEK — PMP QUICK START

On day one of a new project assignment, these actions get your PMP started correctly.

| DAYS 1-3: ORIENT ▸ Read the existing PMP if one exists — note what is current and what is outdated ▸ Read the PDT Charter — who is on it, who has decision authority ▸ Review the scope statement — find In Scope, Out of Scope, and Assumptions ▸ Ask for the WBS — if it does not exist, that is your first gap to close ▸ Identify the current PDBP phase — confirm which PROC governs right now | DAYS 4-7: BUILD OR UPDATE ▸ Open or create the PMP — use the district standard if one exists ▸ Populate what you know now — do not wait for perfect information to start ▸ Flag every section requiring input from a PDT member or functional chief ▸ Schedule a PDT meeting to review the PMP together — make it a team document ▸ Set a review cadence — when will you update the PMP and with whom |
| --- | --- |

THREE QUESTIONS TO ASK YOUR SPONSOR BEFORE YOU FINALIZE SCOPE

Have this conversation before you finalize the scope section. These questions surface what is not in any document.

| 1 | "What does success look like when we hand this project over to you?" Why this works: Surfaces the sponsor's definition of done — often different from the scope statement's definition. |
| --- | --- |
| 2 | "What would make you say this project failed — even if we hit schedule and budget?" Why this works: Surfaces fears and unstated expectations. The answers often reveal scope that was never written down. |
| 3 | "What are you most worried about that I might not know yet?" Why this works: Surfaces institutional knowledge, stakeholder dynamics, and political context the PM needs before planning begins. |

THE PM'S RULE OF THUMB If a decision was made and it is not in the PMP — it does not officially exist. Document it. Update the PMP. Then move on.