STAKEHOLDER ENGAGEMENT PLAN A guide for PMs developing a Stakeholder Engagement Plan for the first time PDBP Phase: Initiation ¦ Governed by: PROC2020 ¦ Reference: EM 5-1-11 ¦ USACE KMP-PPM

KEY PRINCIPLE A stakeholder who is surprised is a stakeholder who becomes a problem. The Stakeholder Engagement Plan (SEP) is how you identify who needs to know what, when, and how — before they find out the wrong way.

WHAT IS THE STAKEHOLDER ENGAGEMENT PLAN — AND WHY IT MATTERS

| THE SEP IS: ▸ A documented plan for identifying, categorizing, and communicating with every party who has a stake in the project ▸ Required under PROC2020 as a component of the Project Management Plan (PMP) ▸ A living document — updated as stakeholders change, relationships evolve, and the project moves through phases ▸ A risk management tool — unmanaged stakeholders are a predictable source of scope conflict, schedule delays, and political interference ▸ The PM's record of intentional relationship management, not reactive damage control | THE SEP IS NOT: ▸ A contact list — it includes engagement strategy, not just names and phone numbers ▸ The Communication Plan — the Communication Plan defines reporting cadence for the PDT; the SEP addresses the broader stakeholder universe ▸ A one-time exercise at initiation — stakeholder dynamics change throughout the project lifecycle ▸ Optional for small projects — every USACE project has stakeholders whose expectations must be managed ▸ Something you build after a stakeholder has already become a problem |
| --- | --- |

THE SEVEN STAKEHOLDER CATEGORIES EVERY USACE PM MUST KNOW

Not every project has stakeholders in every category — but every PM should check all seven before concluding a category is empty. The most common SEP failure is assuming a category has no stakeholders without actually verifying.

▌ INTERNAL USACE STAKEHOLDERS Everyone within USACE who influences or is affected by the project. These are not automatically allies — different divisions have different priorities and timelines. The PM who treats internal stakeholders as given rather than managed will be surprised. ▸ District leadership (District Commander, Deputy Commander, District Engineer) ▸ Deputy Program Manager (DPM) — primary internal interface for the PM ▸ Functional division chiefs — Engineering, Contracting, Real Estate, Planning, Operations ▸ Resident Engineer and construction management staff ▸ Headquarters program office — for projects with HQ oversight thresholds ▸ Division-level leadership — for projects requiring Division Commander concurrence ▸ Resource Management — budget execution and financial reporting chain

▌ PROJECT SPONSOR / END USER The organization or individual who requested the project, funds it (in whole or part), and will use or operate the result. In Military Programs this is typically the installation; in Civil Works it is the non-federal sponsor under a Project Partnership Agreement (PPA). Sponsor expectations are the most frequent source of scope conflict on USACE projects. ▸ Primary sponsor point of contact (usually DPW Director or equivalent) ▸ Installation Commander or equivalent — for significant project decisions ▸ End users — the people who will actually occupy or operate the facility ▸ Installation Management Command (IMCOM) or equivalent oversight body ▸ Non-federal sponsor leadership (Civil Works) — committed under the PPA ▸ Sponsor cost-share representative (Civil Works) — manages the sponsor's financial obligation

▌ CONTRACTOR AND A-E COMMUNITY Firms engaged on the project in design, construction, or support roles. These are not neutral parties — they have interests in schedule, scope, and contract terms that may not align with the government's. Engaging them strategically (not just contractually) produces better outcomes. ▸ Architect-Engineer (A-E) firm — prime and subconsultants ▸ Construction contractor — prime and major subcontractors for significant scopes ▸ Technical review firms (if independent technical review is engaged) ▸ Value Engineering (VE) contractor (if VE study is conducted) ▸ Small business community — for projects with significant small business goals

▌ REGULATORY AND PERMITTING AGENCIES Government agencies with authority to approve, restrict, or stop project activities. These stakeholders operate on their own timelines and priorities. Early engagement prevents schedule surprises that cannot be recovered. ▸ U.S. Army Corps of Engineers Regulatory Division (Section 404/401 permits if applicable) ▸ U.S. Environmental Protection Agency (EPA) ▸ State environmental / historic preservation agencies (SHPO for Section 106) ▸ Utility companies with easements or infrastructure in the project area ▸ Local building and fire inspection authorities (for projects requiring local permits) ▸ Fish and Wildlife Service / NOAA Fisheries (if environmental consultation required) ▸ Federal Aviation Administration (FAA) — for projects near airfields

▌ COMMUNITY AND ADJACENT PROPERTY STAKEHOLDERS Individuals and organizations outside the government who are affected by the project. Often overlooked on military installations but consistently relevant for Civil Works projects and any project with off-installation impacts. Unmanaged community stakeholders can generate political pressure that reaches congressional offices. ▸ Adjacent property owners (for projects with noise, access, or environmental impacts) ▸ Local government (city, county) — especially for Civil Works projects with local cost share ▸ Tribal governments — Section 106 consultation may be required ▸ Environmental and advocacy organizations with interest in the project area ▸ Local business community (for projects affecting access or commerce) ▸ Media — for high-visibility or controversial projects

▌ CONGRESSIONAL AND POLITICAL STAKEHOLDERS Elected officials and their staff who have oversight, appropriations, or constituent interest in the project. For Military Construction, congressional notification requirements apply at specific thresholds. For Civil Works, project authorizations run through Congress. These stakeholders require careful, coordinated engagement — never unilateral. ▸ Congressional members representing the installation or project area ▸ Congressional staff (Armed Services Committees, Appropriations Committees) ▸ State and local elected officials (for high-visibility projects) ▸ Congressional liaison offices within USACE and the parent service ▸ Note: All congressional engagement must be coordinated through the appropriate USACE public affairs and legislative liaison channels

▌ MEDIA AND PUBLIC For most USACE projects, media and public engagement is minimal. However, projects with environmental controversy, community impact, or significant cost can attract public attention that affects the project timeline and political environment. Know the threshold before you reach it. ▸ USACE public affairs officer — primary interface for all media inquiries ▸ Project website or public notices (required for certain permit activities) ▸ Public meetings (required for Environmental Impact Statements and some Civil Works projects) ▸ Social media — primarily a monitoring function; responses coordinated through public affairs ▸ Note: Direct media engagement by the PM without public affairs coordination is not authorized

ENGAGEMENT STRATEGY — THE FOUR APPROACHES

For each stakeholder, assign one of these four engagement strategies. The strategy should reflect both the stakeholder's current stance and the level of influence they have over the project. Strategies are not permanent — review and update at each phase gate.

| Strategy | Typical Stakeholders | What It Means | What You Do |
| --- | --- | --- | --- |
| MONITOR | Low influence, low interest | Aware of the project; not actively engaged; unlikely to affect outcomes. | Track periodically. Notify when project milestones affect them. Do not over-invest resources here. |
| INFORM | Low influence, high interest OR high influence, low interest — needs timely updates | Needs to know what is happening but does not need to be consulted before decisions are made. | Regular one-way communication. Status updates, meeting summaries, milestone notifications. Do not ask for input you will not use. |
| CONSULT | High influence, high interest — provides input before decisions | Has meaningful knowledge or authority that should shape decisions. Must be heard before significant choices are made. | Structured input opportunities. Meetings before decisions, not after. Document what they said and how it was considered. |
| COLLABORATE | Critical influence — co-creates solutions, joint decision-making | The project cannot succeed without their active partnership. Their buy-in is not sufficient — their engagement is essential. | Joint working sessions. Shared ownership of key decisions. Regular direct access to the PM. Treat their constraints as your constraints. |

BUILDING YOUR SEP — FIVE STEPS

| 1 | IDENTIFY — Who has a stake? Start broad. List every person or organization that could affect or be affected by the project. Check all seven categories. Do not filter at this stage — add everyone and reduce later. |
| --- | --- |

| 2 | ANALYZE — What do they need and how much influence do they have? For each stakeholder: What is their primary interest in the project? What is their current stance (supportive, neutral, resistant, unknown)? What is their level of influence over the project? What do they fear? What do they need to stay supportive? |
| --- | --- |

| 3 | PRIORITIZE — Where should you invest your energy? High influence + high interest = top priority. Use the four engagement strategies to categorize. Do not treat all stakeholders equally — that is a resource allocation failure. The sponsor and DPM are always Collaborate. Unknown-stance, high-influence stakeholders need immediate assessment. |
| --- | --- |

| 4 | PLAN — How and when will you engage? For each stakeholder (or category): What is the engagement method (meeting, report, site visit, call)? What is the frequency? Who is the USACE point of contact? What is the key message? What are the trigger events that require immediate outreach? |
| --- | --- |

| 5 | EXECUTE AND UPDATE — Do the work, then revise the plan Engagement is not a checkbox — it is an ongoing activity. Log each significant engagement. Update the SEP at each phase gate, when stakeholder circumstances change, and whenever a stakeholder who was Inform or Monitor starts exhibiting Consult-level concerns. |
| --- | --- |

FOUR SEP FAILURES THAT CREATE PROBLEMS ON USACE PROJECTS

| 1 | The sponsor is treated as a given, not a stakeholder The sponsor signed the PPA or the DD 1391. That does not mean their expectations are understood. CF02 and CF03 in this course demonstrate exactly what happens when sponsor expectations are not surfaced, documented, and managed. Ask the three sponsor alignment questions. Write down the answers. |
| --- | --- |

| 2 | Internal USACE stakeholders are assumed to be aligned Engineering wants the best technical solution. Contracting wants the cleanest solicitation. Operations wants minimal disruption. Real Estate wants time to clear encumbrances. These are not the same priority as the PM's schedule. Internal stakeholder management is not optional. |
| --- | --- |

| 3 | Regulatory agencies are treated as a permitting checklist, not relationships A permit application is a transaction. A relationship with the reviewing agency is a risk mitigation strategy. Agencies that know and trust the USACE team process permits differently than agencies encountering the project for the first time at submission. |
| --- | --- |

| 4 | The SEP is built once and filed Stakeholder circumstances change. A supportive installation commander retires. A neutral community organization becomes engaged. A resistant functional chief gets a new boss. The SEP that was accurate at initiation is rarely accurate at execution. Update it at every phase gate. |
| --- | --- |

THE PM'S STAKEHOLDER RULE A stakeholder relationship that is not actively managed will manage itself — usually at the worst possible moment.

USACE KMP-PPM  |  Stakeholder Engagement Plan Guide  |  Reference: PROC2020 / EM 5-1-11  |  For Official Training Use