SAMPLE SEP — PUBLIC VERSION Engagement plan without stance or influence assessments. Suitable for sharing with stakeholders or filing in accessible project records. See the Sensitive Annex (held separately) for full stakeholder analysis.

STAKEHOLDER ENGAGEMENT PLAN — ENGAGEMENT REGISTER Building 4521 Renovation ¦ Fort Beaumont Military Installation ¦ PUBLIC VERSION P2-123456 ¦ PM: Project Manager, Military Programs Branch ¦ Phase: Initiation ¦ Effective: 15 January 2026

STAKEHOLDER ENGAGEMENT REGISTER

| Code | Category | Role / Stakeholder Group | Strategy | Engagement Method | Frequency | USACE POC | Key Message / Approach |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S-01 | Internal USACE | Deputy Program Manager (DPM) | Col | Direct — weekly check-in; monthly written status | Weekly | PM | Data-first communication. Surface bad news early. Never surprise. Responds well to structured status. |
| S-02 | Internal USACE | District Commander | I | Monthly status through DPM; briefed at major milestones | Monthly via DPM | DPM | On schedule, on budget, no surprises. Brief at milestones only — not day-to-day. |
| S-03 | Internal USACE | FC — Civil / Structural Engineering | C | Bi-weekly PDT meeting; direct coordination on design issues | Bi-weekly | PM | Schedule is the constraint. Needs advance notice of any scope changes affecting structural drawings. |
| S-04 | Internal USACE | Contracting Officer (KO) | C | Pre-award: weekly. Post-award: as needed; all mods through KO | Pre-award: weekly | PM | PM identifies and documents; KO acts. Do not route around KO — it creates liability. |
| S-05 | Internal USACE | Real Estate Specialist | C | Monthly until access confirmed; as-needed thereafter | Monthly | PM | Long queue — engage early. Identify access or easement issues before construction award. |
| S-06 | Internal USACE | Resource Management | I | Monthly financial report; notifications at obligation milestones | Monthly | PM | Keep obligation forecasts current. RM flags projects behind obligation targets. |
| S-07 | Internal USACE | HQ Program Office | M | Triggered only if scope/cost change triggers HQ notification | As triggered | DPM | Not triggered at current scope. Monitor for scope changes crossing threshold. DPM manages HQ relationship. |
| S-08 | Project Sponsor | Primary Sponsor POC — DPW | Col | Monthly briefing (PM leads); direct access for urgent issues; written confirmation of scope decisions | Monthly | PM | Three alignment questions answered and documented. Definition of done may differ from scope statement. Verify at design milestones. |
| S-09 | Project Sponsor | Installation Commander | I | Briefed at major milestones; not day-to-day | Milestone-based | DPM | Protect occupancy date (01 March 2027). If schedule is at risk, brief before it becomes a public issue. |
| S-10 | Project Sponsor | End Users — Building Occupants | C | Pre-design workshop; design review at 35% and 65%; occupancy coordination | At design milestones | PM | End users often have expectations not in the DD 1391. Surface them at the pre-design workshop. Document in writing. |
| S-11 | Project Sponsor | IMCOM / Installation Management | I | Quarterly coordination; notifications for access restrictions or construction impacts | Quarterly | PM | Keep aware of construction schedule and access impacts. Surprises here escalate to installation commander level. |
| S-12 | Contractor / A-E | A-E Firm (prime) | C | Weekly design progress meetings (pre-award); review at 35%, 65%, 95%; RFI response tracking | Weekly pre-award | PM / FC Civil | A-E schedule is on the critical path. Track deliverables weekly. RFI response time is a PM responsibility. |
| S-13 | Contractor / A-E | Construction Contractor (post-award) | C | Weekly construction progress meeting; monthly EVM report; daily COR contact | Weekly post-award | PM / QA Rep | Establish relationship before the first problem. CF07 shows what happens when the PM is reactive. Stay ahead of data. |
| S-14 | Contractor / A-E | Small Business Office | I | Pre-award coordination; semi-annual subcontracting report review | Semi-annual | KO | SB goals are a contracting requirement — KO leads. PM monitors for issues affecting contractor performance. |
| S-15 | Regulatory | State Historic Preservation Office (SHPO) | C | Pre-submission coordination; formal Section 106 submission; response tracking | Per process | Env. Spec. | Do not submit Section 106 without pre-coordination. Pre-submission inquiry complete — no adverse finding expected but formal response required. |
| S-16 | Regulatory | EPA (Region 6) | M | Triggered only if environmental clearance findings change | As triggered | Env. Spec. | Phase I ESA complete — no remediation required. Monitor for subsurface discoveries during construction. |
| S-17 | Regulatory | Installation Safety Office | C | Pre-construction safety plan review; quarterly site visit coordination | Pre-construction + quarterly | Safety Officer | Safety plan submitted 30 days before construction start. Engage proactively — partner, not inspector. |
| S-18 | Regulatory | Utility Companies (3) | C | Pre-construction utility coordination meeting; outage scheduling | Pre-construction | PM / A-E | Three utility crossings identified. Outage coordination must be scheduled 90 days in advance per utility agreements. |
| S-19 | Community | Adjacent Unit Commanders | I | Construction schedule notifications; access restriction alerts | At construction milestones | PM | Service road shared with two adjacent units. Notify before road closures. Keep communication brief and operational. |
| S-20 | Community | Tribal Government (one identified) | C | Section 106 tribal consultation letter sent; response tracking | Per Section 106 process | Env. Spec. | Tribe notified per Section 106 requirements. No response received — send follow-up at 30 days. Do not proceed without documented consultation. |
| S-21 | Congressional | Congressional Representative (District) | I | Standard congressional notifications per MILCON thresholds; no direct PM engagement | Per MILCON requirements | DPM / PAO | Congressional notifications handled through DPM and District PAO. PM does not engage congressional staff directly. |
| S-22 | Congressional | Armed Services Committee Staff | M | Standard threshold notifications only | Per threshold | DPM | No committee-level engagement required at current scope. Monitor for scope changes triggering additional notifications. |

SAMPLE SEP — PUBLIC VERSION  |  For Official Training Use  |  USACE KMP-PPM  |  Reference: PROC2020 / EM 5-1-11